## RICs
Cause	Effect	Impact	Response	Custodian	Dates
					Identification	Occurrence	Closure
In-Team Communication Issues	Poor Efficiency and misunderstandings	Failing to deliver a fully functinal project	Team discussion on possible solutions	Valentin		no	no
Technical issues regarding installing Hyperledger	Inability to work on the project	Failing to deliver a fully functinal project	Seeking help from project's technical advisors
Technical issues with working IPFS network	Inability to work on the project	Failing to deliver a fully functinal project	Seeking help from project's technical advisors
Version control and code syncronisation	Ineficiency and lost data	Failing to deliver a fully functinal project	Using a tested and proven workflow technique
Spending time and resources on insgnificant feautures of the project	Ineficiency and time loss	Failing to deliver a fully functinal project	Carefuly prioritising most important features and focusing on them first
Poor eficiency in general	Time loss and inability to deliver on time	Failing to deliver a fully functinal project	Team discussion on possible solutions
Poor team organisations and task separation	inequal work required from different team members and efficiency problems	failing to deliver a fully functinal project	Planning and assiging tasks carefully
Software updates and issues HLF
Unequal task allocation
Unequal team participation
Team member has COVID-19 or is unwell
Team member can't attend a group meeting